## Test Report
Test Case Summary
Project Name - | https://bangla-reels-frontend.vercel.app/
Module Name - | User Management |  |  |  |  | Total No. | Status
Test Case Version | [6 empty] | PASS
Written By | Imran & Sakib |  |  |  |  | 0 | FAIL
Not Executed
Executed By | Imran & Sakib |  |  |  |  | 0 | Out of Scope
Reviewed By | Imran & Sakib
TEST EXECUTION SUMMARY
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
|  | 0 |  | 0 | 185
Grand Total |  | 0 |  | 0 | 185

## Test Case
Product Name |  | ReelShort | [7 empty] | Pass | 61
Test Case Developed By |  |  | Imran & Sakib | Browser(tested) | [5 empty] | Fail | 0
Test Case Reviewed By |  |  | Imran & Sakib | Performance(tested) | [5 empty] | Not Executed | 4
[10 empty] | Out of Scope | 0
[10 empty] | Total | 65
TC_ID | Sprint | Module | Features | Test Cases | Expected Result | Actual Result | Step Desription | Test Data | Bug Screen Shot | Final Status | Remarks
TC01 |  | Sign up | Sign up | First name | [5 empty] | Not a bug
TC02 |  |  |  | Last name | [5 empty] | Pass
TC03 |  |  |  | Email address | [5 empty] | Not a bug
TC04 |  |  |  | Password | [5 empty] | Reopen
TC05 |  | Log in | Log in | Valid email | [5 empty] | Resolved
TC06 |  |  |  | Valid password | [5 empty] | Close
TC07 |  |  |  | Invalid email | [5 empty] | Pending
TC08 |  |  |  | Invalid password | [5 empty] | Unable to test
TC09 |  |  |  | Forgot password | [5 empty] | Pass othes issue
TC10 |  |  |  | Reset password | [5 empty] | Pass
TC11 |  | Home | Nevigate button | Left move click | [5 empty] | Pass
TC12 |  |  |  | Right move click | [5 empty] | Pass
TC13 |  |  | View all | All videos showing | [5 empty] | Pass
TC14 |  |  | Add play list | Single video add | [5 empty] | Pass
TC15 |  |  |  | Multiple video add | [5 empty] | Pass
TC16 |  |  | Scroll Side mouse side bar | Left scroll | [5 empty] | Pass
TC17 |  |  |  | Right scroll | [5 empty] | Pass
TC18 |  | About | Terms of Service | Showig all Terms of Service info | [5 empty] | Pass
TC19 |  |  | Privacy Policy | Showig all Privacy Policy info | [5 empty] | Pass
TC20 |  |  | Contact Us | Showig all Contact Us info | [5 empty] | Pass
TC21 |  | Support | Feedback | Showig all Feedback info | [5 empty] | Pass
TC22 |  |  | Media and Public Relation | Showig all Media and Public Relation | [5 empty] | Pass
TC23 |  | Community | Linkedin | Show to the linkedin community
TC24 |  |  | Twiter | Show to the Twiter community
TC25 |  |  | Facebook | Show to the Facebook community
TC26 |  |  | Instagram | Show to the Instagram community
TC27 |  |  | Youtube | Show to the Youtube community
TC28 |  | Download | Qr code | Show to the valid Qrcode
TC29 |  | Categories | Categories | Single category
TC30 |  |  |  | All category
TC31 |  | Categories (Identites) | Subcategories (Identites, story beats,gerns,Tag) | Sho all the sub category
TC32 |  |  | Sort by (Popular,latest) | Single click and multiple click sort
TC33 |  |  | bookmark | Video add to book mark
TC34 |  |  | Play video | play video single click and multiple click
TC35 |  | Categories (Story_Beats) | Story_Beats | Show all the story single and multiple story
TC36 |  |  | Sort by (Popular,latest) | Single click and multiple click sort
TC37 |  |  | bookmark | Video add to book mark
TC38 |  |  | Play video | play video single click and multiple click
TC39 |  | Categories (Genres) | Categories (Genres) | Sho all the genres
TC40 |  |  | Sort by (Popular,latest) | Single click and multiple click sort
TC41 |  |  | bookmark | Video add to book mark
TC42 |  |  | Play video | play video single click and multiple click
TC43 |  | Categories (Tags) | Categories (Tags) | Sho all the genres
TC44 |  |  | Story Beat Types | Show all the types
TC45 |  |  |  | Single click and multiple click sort
TC46 |  |  |  | Video add to book mark
TC47 |  |  |  | play video single click and multiple click
TC48 |  | Fandom | Show all the vlogs | Show single vlog and multiple vlog
TC49 |  |  |  | Single vlog
TC50 |  | Fandom vlog details | Fandom vlog details | Show all the fandom vlog details
TC51 |  |  | Person profile name | Show to the person profile name
TC52 |  |  | Date | Show to the vlog date
TC53 |  |  | Description | Show full description with uploaded image
TC54 |  |  | Watch no button | Redirect to app page
TC55 |  |  | Leave a comment | Show to the leave a comment
TC56 |  |  | Save comment | Click save singe and multiple
TC57 |  |  | All comments | Show all the comment
TC58 |  |  | Download (QR) | Scan and show to the Qrcode
TC59 |  |  | Recent Posts | Show all the recent posts
TC60 |  | Contest | Overview | All overview info showing
TC61 |  |  | Enter the contest | Show all the contest info
TC62 |  |  | Rules | Show all the rules
TC63 |  |  | Format | Show all single formats
TC64 |  |  | Upload Episodes | Show all the single upload
TC65 |  |  |  | Show all the multiple upload
TC66 |  |  | Film Details | Show all the details info
TC67 |  |  | Select a theme | Theme select
TC68 |  |  |  | Theme unselect
TC69 |  |  | Confirmation | Work full Confirmation
TC70 |  |  | Cancel | Cancel the contest
TC71 |  |  | Continue | Continue the contest
TC72 |  | Top List | Today | Show all today list
TC73 |  |  | Week | Show all week list
TC74 |  |  | Month | Show all month list
TC75 |  | Serch | Serch | Search valid video
TC76 |  |  |  | Search invalid video
TC77 |  | Laguage | English | Showing english language
TC78 |  |  | Bangla | Showing bangla language
TC79 |  |  | Others | Showing others language
TC80 |  | History | History | Showing all history
TC81 |  |  | My List | All selected my list
TC82 |  |  | More | Show all the more hostory
TC83 |  | Profile | Guest | Showing to the guest info
TC84 |  |  | Coins | Show to the all coins
TC85 |  |  | Bonus | Show to the all bonus
TC86 |  |  | Top up | Show to the all Top up
TC87 |  | Guest Profile Overview | Last Activity | Show all Prfiles last activity
TC88 |  |  | hours ago | how many hours ago
TC89 |  |  | Coins | Show to the all coins
TC90 |  |  | Episodes | Show to the all episodes
TC91 |  |  | Saved | Show to the saved info
TC92 |  | Recommended | Video play | Play all the video
TC93 |  |  | bookmark | Added bookmark to the video
TC94 |  |  | Recent Activity | Show to the all recent activity
TC95 |  |  | View all activity | View all activity for recommended
TC96 |  | Subscription & Rewards | My Wallet | Show to the all wallet
TC97 |  |  | Coins | Show to the all coins
TC98 |  |  | Reward Coins | Show to the all Topup
TC99 |  |  | Topup | Show to the all rewards coins
TC100 |  |  | Reelshort Membership | All membership showing
TC101 |  |  | Active now | Show active now
TC102 |  |  | Transactionhistory | Show to the all Transactionhistory
TC103 |  |  | Type | Show to the all Type
TC104 |  |  | Amount | Show to the all Amount
TC105 |  |  | Coin Plan | Show to the all coin plan
TC106 |  |  | Method | Show to the all method
TC107 |  |  | Status | Show to the all status
TC108 |  |  | Date | Show to the all date
TC109 |  | My List | Play video | Play on video
TC110 |  |  | bookmark | Added bookmark to the video
TC111 |  |  | Video details page | Show to the All video detais
TC112 |  | Video details page | Details | Show to the video details
TC113 |  |  | Video Type | All the types video showing
TC114 |  |  | Date | Show to the all date
TC115 |  |  | Video watch | Timely video watch
TC116 |  |  | Video share | Timely video share
TC117 |  |  | Description | Show to the all Description
TC118 |  |  | Selections | Workon selection plane for click
TC119 |  |  | Auto play | Work on auto play when on toggle button
TC120 |  |  | See less | Show to the all see less
TC121 |  |  | See More | Show to the all see more
TC122 |  |  | You may like | Show to the you may like
TC123 |  |  | Home | Show to the all Home info
TC124 |  |  | Collateral Hearts | Show to the all Collateral Hearts
TC125 |  |  | Episode | Single episode and multiple episode
TC126 |  | Collateral Hearts | Play video | Play on time video
TC127 |  |  | Love rection | Click on love reaction and react
TC128 |  |  | Share link | Work on share link and share to the link
TC129 |  |  | Category | Show to the all category
TC130 |  |  | Go watching | Work on go watching and click on view
TC131 |  |  | Download | Show downloaded file and view all downloads
TC132 |  |  | Episode List | Show to the Episode List
TC133 |  |  | You May Like | Show to the all You May Like
TC134 |  |  | Play video | Click on play and single click for single play
TC135 |  |  | bookmark | Show to the all bookmark
TC136 |  | My submission | Your current contest status | Show to the all current contest status
TC137 |  |  | Review Status | Change review status current and changed
TC138 |  |  | Theme | Change current theme and new theme
TC139 |  |  | Uploaded on | Upload many types of videos
TC140 |  |  | Review time left | Show to the all review time left
TC141 |  |  | Viewdetails | Show all the video details
TC142 |  |  | 3 dots section | Show to the all 3 dots
TC143 |  |  | Edit | Edit current status
TC144 |  |  | Add new | Add new submission file
TC145 |  | Analytics | Total Views | Show all Total Views
TC146 |  |  | Total Watchtime | Show all Total Watchtime
TC147 |  |  | Average Watch Duration | Show all Average Watch Duration
TC148 |  | Analytics Views Trend | This week | Show all Analytics This week
TC149 |  |  | This month | Show all Analytics This month
TC150 |  |  | This year | Show all Analytics This year
TC151 |  |  | All Time | Show all Analytics All Time
TC152 |  | Analytics Watchtime Trend | This week | Show all Analytics This week
TC153 |  |  | This month | Show all Analytics This month
TC154 |  |  | This year | Show all Analytics This year
TC155 |  |  | All Time | Show all Analytics All Time
TC156 |  | Analytics Video Performance Breakdown | Thumbnail | Current thumbnail change and show all thumbnail
TC157 |  |  | Title | Show all Title
TC158 |  |  | Views | Show all Views
TC159 |  |  | Watchtime (hrs) | Show all Watchtime (hrs)
TC160 |  |  | Avg. Watch Duration | Show all Avg. Watch Duration
TC161 |  |  | Position | Show all Position
TC162 |  | Earning | This Month’s Earnings | Show all This Month’s Earnings
TC163 |  |  | Pending Payout | Show all pending layout
TC164 |  |  | Total Earnings | Show all Total Earnings
TC165 |  | Earning Chart | Last month | Show to the last month earning chart
TC166 |  |  | Last 3 | Show to the 3 month earning chart
TC167 |  |  | Last 6 | Show to the 6 month earning chart
TC168 |  |  | Last 12 | Show to the 12 month earning chart
TC169 |  | Earnings Summary | Video | All the Earnings Summary video singly show
TC170 |  |  | Title | Show all Title
TC171 |  |  | Views | Show all Views
TC172 |  |  | Watchtime (hrs) | Show all Watchtime (hrs)
TC173 |  |  | Earnings | Show all Earnings
TC174 |  |  | Date | Show all single date and changed date current date
TC175 |  | Earning Payment History | Transaction ID | Single Transaction ID and multiple Transaction ID
TC176 |  |  | Amount | Show all Amount
TC177 |  |  | Method | Show all Method
TC178 |  |  | Status | Show all Status
TC179 |  |  | Date | Show all single date and changed date current date
TC180 |  | Feedback | Feedback link copy | Copied to the feedback link single click
TC181 |  |  | Email | Show all Email
TC182 |  |  | Feedback | Show all Feedback
TC183 |  |  | Pictures Upload | Upload single picture and multiple picture
TC184 |  |  | Confirm | Single click on confirm button send feedback
TC185 |  |  |  | Invaid data with send feedback

## Bug Report
Date | Test Case ID | Issue_ID | Issue | Module | Features | Screenshoot | QA By | Assigned To | Issue Solved By | Issue Solved By | Current Status | Bug Priority Level
[7 empty] | Imran | Tanvir | Tanvit | N/A | Dev | Medium
[7 empty] | Imran | UI | UI | Tanvir | Stagging | Low
[7 empty] | Imran | N/A | N/A | UI | Production | Medium
[7 empty] | Imran |  |  | Tanvir | Testing-Beta | High
[7 empty] | Imran |  |  | N/A |  | Low
[7 empty] | Imran |  |  | N/A |  | Medium
[7 empty] | Sakib |  |  | N/A
[7 empty] | Sakib |  |  | N/A
Sakib

## New Bug Report
Test Case ID | Module | Issue | Bug Type | Screenshoot | QA By | Assigned To | Issue Solved By | Current Status | Bug Priority Level | Status | Comment
1 | Payment | all payment method are not working properly | Functional | all payment method are not working properly.png | Sakib | N/A | Tanvit | Dev | Medium
2 | Catagory | In Category → Category List, when a category is activated, the change is not reflected in the Navbar category section | Functional | In Category → Category List, when a category is activated, the change is not reflected in the Navbar category section.png | Sakib | Abu Bokor | Abu Bokor | Production | Low | Reopen
3 |  | In Coin Plan Purchase, reward coins are not reflected in the user balance after successful payment. | Functional | In Coin Plan Purchase, reward coins are not reflected in the user balance after successful payment..png | Sakib | N/A | N/A | Production | Medium
4 | Package | In Package Management → Add new Coin Plan, Make proper validation Massage in Description Field | Functional | In Package Management → Add new Coin Plan, Make proper validation Massage in Description Field.png | Sakib | Naimur | Naimur | Testing-Beta | High | Close
5 | Package | In Package Management → Add New Coin Plan, the same coin plan can be added multiple times. | Functional | In Package Management → Add New Coin Plan, the same coin plan can be added multiple times..png | Sakib | N/A |  |  | Low
6 | Package | In Package Management → Add new Subscription plan, Make proper validation Massage in Description Field | Functional | In Package Management → Add new Subscription plan, Make proper validation Massage in Description Field.png | Sakib | Naimur | Naimur |  | Medium | Close
7 | Package | In Package Management → add search bar massage for user friendly | Functional | In Package Management → add search bar massage for user friendly.png | Sakib | Naimur | Naimur |  |  | Close
8 | Package | In Package Management → Cannot add a new Subscription Plan | Functional | In Package Management → Cannot add a new Subscription Plan.png | Sakib | Sarwar | Sarwar | Production | High | Resolved
9 | Package | In Package Management → Coin Plan, the ‘Is Popular’ toggle does not work properly and has no effect on the user view. | Functional | In Package Management → Coin Plan, the ‘Is Popular’ toggle does not work properly and has no effect on the user view..png | Sakib | Abu Bokor | Abu Bokor |  |  | Close
10 | Package | In Package Management → Subscription Plan → All toggle buttons not working properly | Functional | In Package Management → Subscription Plan → All toggle buttons not working properly.webm | Sakib | Sarwar |  |  | High
11 |  | In Subscription & Rewards → Payment Method, the UI placement of elements is not user-friendly | Functional | In Subscription & Rewards → Payment Method, the UI placement of elements is not user-friendly.png | Sakib | Sarwar | Sarwar | Production | Medium | Resolved
12 |  | In the Sub Category List→Description Form Validation, validation messages are not user-friendly | UI | In the Sub Category List→Description Form Validation, validation messages are not user-friendly.png | Sakib | Naimur | Naimur |  |  | Close
13 |  | In the Sub Category List→Sub Category List, add Proper validation and messages . | Functional | In the Sub Category List→Sub Category List, add Proper validation and messages ..png | Sakib | Naimur | Naimur |  |  | Close
14 |  | In TOP up → Pricing, the Offer Price and Main Price are displayed incorrectly in the UI | Functional | In TOP up → Pricing, the Offer Price and Main Price are displayed incorrectly in the UI.png | Sakib | Riyal | Sarwar | Production | High | Close
15 |  | make Highest limit of Feedback,Not minimum | Functional | make Highest limit of Feedback,Not minimum.png | Sakib | Naimur | Naimur |  | High | Close
16 |  | Membership, incorrect data is shown in the membership details | Functional | Membership, incorrect data is shown in the membership details.png | Sakib | N/A
17 |  | Order meheod data are shown incorrect | Functional | Order meheod data are shown incorrect.png | Sakib | N/A
18 |  | payment input field backspace are incorrect working | Functional | payment input field backspace are incorrect working.webm | Sakib | N/A
19 |  | Total Coins, purchased coins are not added to the user’s total coin balance. | Functional | Total Coins, purchased coins are not added to the user’s total coin balance..png | Sakib | N/A
20 |  | wrong information shown in payment successfull window | Functional | wrong information shown in payment successfull window.webm | Sakib | Naimur
21 |  | In fandom List is published and archived toggled button issue | Functional | In fandom List is published and archived toggled button issue.png | Sakib | Abu Bokor | Abu Bokor | Production |  | Close
22 | Category management | Even though it’s set to show 10 items per page, only 4 are being displayed. | UI | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
23 |  | In the discount field, data can be saved even when a negative value is entered. | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production | Medium | Resolved
24 |  | Is it possible to submit without entering the time | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production | High | Close
25 |  | The modal should close when all categories are selected | UI | Bugsrc | Imran | Sarwar | Sarwar |  |  | Close
26 |  | Turning off 'Is Archived' from the content list does not work | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
27 |  | When 'Content Published' is turned on from off, the text should display 'Content Published | UI | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
28 |  | In the Performer List, if the text in the actor list is too large, it breaks the layout | UI | Bugsrc | Imran | Naimur | Naimur |  |  | Close
29 | Coin plan | After entering an invalid discount code, clicking on “Pay Now” still redirects to the payment gateway page | Functional | Bugsrc | Imran | N/A
30 |  | When an invalid discount code is entered, it should display a message like “Invalid discount code” instead of “Something went wrong.” | Functional | Bugsrc | Imran | Sarwar | Sarwar |  |  | Close
31 | Subscription plan | On the Subscription page, after clearing the filter, all items should be displayed. | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor |  |  | Close
32 |  | The calendar should be activated | UI | Bugsrc | Imran | Abu Bokor |  |  | High
33 |  | The calendar should be activated | UI | Bugsrc | Imran | Abu Bokor |  |  | High
34 | Fandom (Comment box) | In the Fandom comment section, submitting a long comment shows an error. | Functional | Bugsrc | Imran | Naimur | Naimur |  |  | Close
35 |  | Validation needs to be added in the content management section | Functional | Bugsrc | Imran | Sarwar | Sarwar |  |  | Resolved
36 |  | Currentcy shows bdt when payment completed | Functional | Currentcy.jpg |  | Naimur | Naimur |  |  | Resolved
37 |  | Reward management are not working | Functional | Reward management are not working.webm | Sakib | N/A
38 |  | add Section management's search bar massage | UI | add Section management's search bar massage.png | Sakib | Naimur | Naimur |  |  | Reopen | new
39 |  | Add Fandom Management's search bar Massage | Functional | Add Fandom Management's search bar Massage.png | Sakib | Naimur | Naimur |  |  | Reopen | new
40 |  | add new discount are not working properly | Functional | add new discount are not working properly.png | Sakib | Abu Bokor |  | Production |  | Close | New
41 |  | In Discount Management → Discount List, the update function does not work properly. | Functional | In Discount Management → Discount List, the update function does not work properly..png | Sakib | Abu Bokor |  | Production | Medium | Close | new
42 |  | add proper searchbar massage in currency,discount and report setting | Functional | add proper searchbar massage in currency,discount and report setting.png | Sakib | Naimur | Naimur |  |  | Reopen | new
43 | Actor | Adding an actor causes an error message to show up | Functional | Bugrc | Imran | Sarwar |  |  | Medium
44 |  | When a category is selected, it still remains in the category list | Functional | Bugsrc | Imran | Sarwar |  |  |  | Close
45 | Fandom List (Cover image) | In the fandom list, the cover page image preview is broken | UI | Bugsrc | Imran | N/A
46 |  | In the fandom list, after uploading an image, clicking the cross button shows “received null. | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor |  |  | Close
47 |  | Embed Link not working | Functional | Embed Link not working.png | Sakib | Sarwar |  |  | Low
48 |  | when share any reel its not showing the thumble img | Functional | when share any reel its not showing the thumble img.png | Sakib | N/A
49 |  | Wishlist not working properly | Functional | Wishlist not working properly.webm | Sakib | Naimur |  |  | High
50 |  | add validation for banner section not showing multiple times | Functional | add validation for banner section not showing multiple times.png | Sakib | Abu Bokor | Abu Bokor |  |  | Close
51 |  | After updating banner img,but showing missing | Functional | After updating banner img,but showing missing.png | Sakib | Sarwar |  |  | High
52 |  | Home page search bar ,not showing thumble img | Functional | Home page search bar ,not showing thumble img.png | Sakib | N/A
53 |  | In content manageent,banner img are not showing | UI | In content manageent,banner img are not showing.png | Sakib | Sarwar | Sarwar |  |  | Close
54 |  | in section layout thumble img not showing | UI | in section layout thumble img not showing.png | Sakib | N/A
55 |  | like button not working | Functional | like button not working.png | Sakib | Sarwar |  |  | High
56 | Section Management | A section can be created even without selecting a display position — validation needs to be added | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
57 |  | If Display Position is not provided, a toast message should appear saying "Display position required | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
58 |  | Is this section still static, or has it been made dynamic now | UI | Bugsrc | Imran | Sarwar |  |  | Medium
59 |  | A Network Error occurs in the Episode section | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
60 |  | If it’s showing 5/5 by default, that’s a logic issue — you should fix it so that ratings only appear after actual user input | Functional | Bugsrc | Imran | Naimur |  |  | High
61 |  | Even after turning the Section Status off, the section still appears on the webpage | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
62 |  | The total content and display order are not showing; I left them blank and saved | Functional | Bugsrc | Imran | Abu Bokor | Abu Bokor | Production |  | Close
63 |  | Contest managment date issue | Functional | Contest managment date issue.webm | Sakib | Naimur
64 |  | in content management episod archived toggle button not working | Functional | in content management episod archived toggle button not working.png | Sakib | Sarwar
65 |  | in contest management,Show a validation massage for rules field | Functional | in contest management,Show a validation massage for rules field.png | Sakib | Naimur
66 |  | in content management episod published toggle button not working | Functional | in content management episod published toggle button not working.png | Sakib | Sarwar
67 |  | Date filed issue in add new contest management | Functional | Date filed issue in add new contest management.png | Sakib | Contest
68 |  | in content management episod published toggle button not working | Functional | in content management episod published toggle button not working.png | Sakib | Sarwar
69 |  | in contest management,Show a validation massage for rules field | Functional | in contest management,Show a validation massage for rules field.png | Sakib | Naimur
70 |  | when add a new Perform,it showing error | Functional | when add a new Perform,it showing error.png | Sakib | Abu Bokor | Abu Bokor | Production | High | Pass othes issue | new
71 |  | Autoplay button not working | Functional | Autoplay button not working.png | Sakib | Abu Bokor |  | Production | High | Resolved
72 |  |  | Functional |  | Sakib
73 |  | In My Submission section, the ‘Add New’ button does not work. | Functional | In My Submission section, the ‘Add New’ button does not work..png | Sakib
74 |  | In My Submission section, the ‘three dot’ button does not work. | Functional | In My Submission section, the ‘three dot’ button does not work..png | Sakib
75 |  | In Package Management → Add Coin Plan, the input fields are not user-friendly. | Functional | In Package Management → Add Coin Plan, the input fields are not user-friendly..png | Sakib | Abu Bokor | Abu Bokor |  |  | Close
76 |  | New discount cupon cannot use when topup | Functional | New discount cupon cannot use when topup.png | Sakib
77 |  | Responsive issue in payment section | Responsive | Responsive issue in payment section.png | Sakib | Riyal | Riyal | Production |  | Close
78 |  | Episode details are not showing properly in mobile responsive | Functional | Episode details are not showing properly in mobile responsive.webm | Sakib | Sarwar |  |  | High
79 |  | Contest entries doesnot work | Functional | Contest entries doesnot work.webm | Sakib | Abu Bokor | Abu Bokor | Production |  | Close
80 |  | Chnage password functionality doesnot work | Functional | Chnage password functionality doesnot work.png | Sakib | Abu Bokor |  |  | High
81 |  | Episodes unlocked layout break | Responsive | Episodes unlocked layout break.png | Sakib | Riyal | Riyal | Production | Medium | Close
82 |  | The discount is created successfully, but it does not appear on the mobile view. | Functional | Bugsrc | Imran | N/A |  |  |  |  | It's take time to fetch after new data create, that's why loading.
83 |  | The user layout is broken in the All Users section | UI | Bugsrc | Imran | Riyal | Riyal | Production | Medium | Close
84 |  | After creating a coin, the View Details option doesn’t appear on mobile | Functional | Bugsrc | Imran | N/A |  |  |  |  | Kindly recheck this
85 |  | In the Subscription and Reward section, the payment type layout is broken | UI | Bugsrc | Imran | N/A
86 |  | The "Cancel" and "Remove Story" button layout in the My List section is broken | UI | Bugsrc | Imran | Naimur |  |  | Medium
87 |  | The love reaction in the Content section is not working | Functional | Bugsrc | Imran | N/A |  |  |  |  | Only works in episode details page, In content details just show.
88 |  | When commenting on content from the History section, it shows “undefined | Functional | Bugsrc | Imran | Abu Bokor |  | Production |  | Close
89 |  | When commenting on content from History, the toast and modal do not close; they only close when the page is reloaded | Functional | Bugsrc | Imran | Abu Bokor |  | Production |  | Close
90 |  | It shows a 404 error in the Category section | Functional | Bugsrc | Imran | Naimur |  |  | High
91 |  | The Admin Panel remains selected in the sidebar | Functional | Bugsrc | Imran | N/A
92 |  | Even after uploading a contest, it does not appear | Functional | Bugsrc | Imran | N/A
93 |  | In the Overview, the 'Recommended for You' content shows as undefined. | Functional | Bugsrc | Imran
94 |  | After changing the language from the sidebar, the spacing has decreased | UI | Bugsrc | Imran | Riyal
95 |  | The content is playing, but it shows 'Screen Capture Blocked | Functional | Bugsrc | Imran | N/A
96 |  | The History section in the sidebar does not respond to any actions | Functional | Bugsrc | Imran | Naimur |  |  | High
97 |  | The content image is not displaying | Functional | Bugsrc | Imran
98 |  | Img layout mismatch in contest | Functional | Img layout mismatch in contest.png | Sakib | Naimur |  |  | Urgent
99 |  | In All Contest → Edit Award, the ‘Is active’ button is not working | Functional | In All Contest → Edit Award, the ‘Is active’ button is not working.png | Sakib | Riyal | Riyal | Production | Urgent | Not a bug | In design there were some button included but Buttons are no longer nedd after functionality implementation
100 |  | In All Contest → Edit phase, the ‘Is active’ button is not working | Functional | In All Contest → Edit phase, the ‘Is active’ button is not working.png | Sakib | Riyal | Riyal | Production | Urgent | Not a bug | In design there were some button included but Buttons are no longer nedd after functionality implementation
101 |  | In All Contest → User View, the ‘View Details’ button on the contest card has a UI mismatch. | UI | In All Contest → User View, the ‘View Details’ button on the contest card has a UI mismatch..png | Sakib | Naimur | Naimur |  | Urgent | Reopen | Remove existing description, then create new description
102 |  | in contest details img position incorrect | UI | in contest details img position incorrect.png | Sakib | Naimur |  |  | Urgent
103 |  | in contest details,mobile responsive are not complete | Responsive | in contest details,mobile responsive are not complete.png | Sakib | Naimur |  |  | Urgent
104 |  | In Contest Management → Awardadding a Award creates multiple duplicate awardat the same time. | Functional | In Contest Management → Awardadding a Award creates multiple duplicate awardat the same time..webm | Sakib | Riyal | Riyal | Production | Urgent | Close
105 | Contest Management | In Contest Management → Contest List, the Active toggle button does not respond or update status | Functional | In Contest Management → Awardadding a Award creates multiple duplicate awardat the same time..webm | Sakib | Riyal |  |  | Urgent
106 |  | In Contest Management → Theme, adding a new Contest pahse creates multiple duplicate Contest pahse at the same time. | Functional | In Contest Management → Theme, adding a new Contest pahse creates multiple duplicate Contest pahse at the same time..webm | Sakib | Riyal | Riyal | Production | Urgent | Close
107 |  | In Contest Management → Theme, adding a new theme creates multiple duplicate themes at the same time. | Functional | In Contest Management → Theme, adding a new theme creates multiple duplicate themes at the same time..webm | Sakib | Riyal | Riyal | Production | Urgent | Close
108 |  | In Contest Management → Theme, adding a new theme creates multiple duplicate themes at the same time. | Functional | proper validation and msg are missing in the add new phase's date field input field.png | Sakib | Riyal | Riyal | Production | Urgent | Close
109 |  | in contest details page layout and all content incorrect | UI | in contest details page layout and all content incorrect.png | Sakib | Naimur |  |  | High
110 |  | proper validation and msg are missing in the add new phase's phase title input fi | Functional | proper validation and msg are missing in the add new phase's phase title input fi.png | Sakib | Riyal | Riyal | Production | Urgent | Close
111 |  | proper validation is missing in the Award Title input field | Functional | proper validation is missing in the Award Title input field.png | Sakib | Riyal | Riyal | Production | Urgent | Close
112 |  | proper validation is missing in the Enter Contest Title input field | Functional | proper validation is missing in the Enter Contest Title input field.png | Sakib | Riyal | Riyal | Production | Urgent | Close
113 |  | proper validation is missing in the Episode details Title input field | Functional | proper validation is missing in the Episode details Title input field.png | Sakib | Sarwar |  |  | High
114 |  | proper validation is missing in the Theme Title input field | Functional | proper validation is missing in the Theme Title input field.png | Sakib | Riyal | Riyal | Production | Urgent | Close
115 |  | Responsive missing in contest pages | Responsive | Responsive missing in contest pages.png | Sakib | Naimur |  |  | High
116 |  | when delete theme poster its show something wrong | Functional | when delete theme poster its show something wrong.webm | Sakib | Riyal |  | Dev | Urgent | Inprogress
117 |  | when navigating back to the previous page, the uploaded image data is cleared. | Functional | when navigating back to the previous page, the uploaded image data is cleared..webm | Sakib | Sarwar |  |  | Urgent
118 |  | when upload a video in contest its showing something wrong msg | Functional | when navigating back to the previous page, the uploaded image data is cleared..webm | Sakib | Sarwar |  |  | Urgent
119 | Reward management | It shows “Invalid Input. | Functional | Bugsrc | Imran
120 |  | In the “Add Daily Coin Reward” section, it shows “Invalid Input | Functional | Bugsrc | Imran
121 |  | In the Edit Daily Coin Reward section, it shows “Invalid Input. | Functional | Bugsrc | Imran
122 | Feedback | In the Feedback section, multiple images are not showing after submission | Functional | Bugsrc | Imran
123 |  | In the Feedback section, when trying to delete an item, it doesn’t get deleted | Functional | Bugsrc | Imran
124 |  | The profile layout is broken | Functional | Bugsrc | Imran
125 |  | Can I select today’s date and a previous date | UI | Bugsrc | Imran
126 | Content management | In the episode list, uploaded episodes don’t appear, but they show up when going to “Go Watching | Functional | Bugsrc | Imran
127 |  | Validation needs to be added | Functional | Bugsrc | Imran
128 |  | The image is not displaying on the Video Details page | Functional | Bugsrc | Imran
129 |  | in discount section,Max Redemtions logic not working | Functional | in discount section,Max Redemtions logic not working.png | Sakib | Ashikur Rahman |  |  | High
130 | Discount | in discount section,Current Redemtions value not changed | Functional | in discount section,Current Redemtions value not changed.png | Sakib | Ashikur Rahman |  |  | High
131 |  | in discount section,Fixed amount value not added in discount | Functional | in discount section,Fixed amount value not added in discount.png | Sakib | Ashikur Rahman |  |  | High